## Connection Cost Guidance
No. | Cost item | Average ($) of the nameplate capacity of projects ≤ 250kW | [5 empty] | Note on potentially high variability factors affecting the cost item
|  | Single Phase |  |  | Three Phase
|  | 0-12kW | 12kW-30kW | 30kW-150kW | 0-12kW | <15kV:12kW-50kW >15kV:12kW-100kW | Upto 250kW
1 | Material | 156.78 | 279.64 | 279.64 | 846.99 | 946.74 | 946.74 | The price could change based on the type of meter used
2 | Labour | 499.04 | 499.04 | 499.04 | 499.04 | 499.04 | 499.04
3 | Equipment | 56 | 56 | 56 | 56 | 56 | 56
4 | Admin/Handling Fee | 78.41 | 96.84 | 96.84 | 181.94 | 196.91 | 196.91
5 | Meter Recovery Credit | -88.64 | -88.64 | -88.64 | -434.77 | -434.77 | -434.77
6 | NPEI CIA Fees | - | 500 | 2500 | - | 500 | 2500
| Total connection cost | 701.59 | 1342.88 | 3342.88 | 1149.2 | 1763.92 | 3763.92
Notes: 1. This does not include the upstream transmitter CIA Fees as it could vary based on if TA is available. 2. For HONI CIA Fees details, visit the HONI website at https://www.hydroone.com/business-services/commercial-industrial-generators-and-ldcs/connection-impact-assessment. 2. This does not include any system upgrade cost, i.e. transformer or pole upgrade, etc. These costs will be provided in the Offer to Connect issued to the customer. 3. This does not include SCADA monitoring and transfer trip costs as they are not requried for projects ≤ 250kW.

## Sample Cost Variance Guidance
DER Group/kW Size Range | No. | Project type (exporting/non-exporting) | Connection Cost Estimate ($) | Actual Connection Cost ($) | Variance [Actual-Estimate] ($) | Variance % | Expansion required (Y/N) | Transfer Trip required (Y/N) | Build & Energization duration (Months) | General Notes
Group 1: 0-12 kW (Micro-DER) | 1 | Exporting | 792.8 | 792.8 | 0 | 0% | N | N | 2
| 2 | Non-Exporting | 792.8 | 792.8 | 0 | 0% | N | N | 5
Group 2: 12-250 kW | 1 | Exporting | 1342.53 | 1342.53 | 0 | 0% | N | N | 5
| 2 | Non-Exporting | 1298.6 | 1298.6 | 0 | 0% | N | N | 7
Group 3: >250 kW | 1 | Non-Exporting | 67579.76 | 46953.06 | -20626.7 | -30.52% | N | Y | 6 | This includes the SCADA monitoring and transfer trip cost. The transfer trip was with another LDC, not Hydro One.